## Sheet1
Project management - Gantt Chart
Tasks | Start date | Duration (days) | End date
Background | 2023-10-16 | 90 | 2024-01-14
Literature review | 2023-10-16 | 45 | 2023-11-30
Researching ML algorithms | 2023-11-05 | 50 | 2023-12-25
Learning how to use Python tools | 2023-11-20 | 54 | 2024-01-13
Design (requirements, specification) | 2023-10-30 | 24 | 2023-11-23
Implementation | 2023-12-27 | 105 | 2024-04-10
Data exploration and visualisation | 2023-12-27 | 26 | 2024-01-22
Iterative development prototype 1 | 2024-01-15 | 25 | 2024-02-09
Prototype 1 evaluation and improvements | 2024-02-09 | 8 | 2024-02-17
Iterative development prototype 2 | 2024-02-17 | 20 | 2024-03-08
Prototype 2 evaluation and improvements | 2024-03-08 | 5 | 2024-03-13
Iterative development prototype 3 | 2024-03-13 | 13 | 2024-03-26
Prototype 3 evaluation and improvements | 2024-03-26 | 6 | 2024-04-01
Testing and validation | 2024-04-01 | 11 | 2024-04-12
Report writing | 2023-11-20 | 156 | 2024-04-24
Progress report | 2023-11-20 | 21 | 2023-12-11
Final report | 2024-02-24 | 60 | 2024-04-24
|  |  |  | Tasks | Month | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April
[5 empty] | Week | Week 1 [02/10] | Week 2 [09/10] | Week 3 [16/10] | Week 4 [23/10] | Week 5 [30/10] | Week 6 [06/11] | Week 7 [13/11] | Week 8 [20/11] | Week 9 [27/11] | Week 10 [04/12] | Week 11 [11/12] | Week 12 [18/12] | Week 13 [25/12] | Week 14 [01/01] | Week 15 [08/01] | Week 16 [15/01] | Week 17 [22/01] | Week 18 [29/01] | Week 19 [05/02] | Week 20 [12/02] | Week 21 [19/02] | Week 22 [26/02] | Week 23 [04/03] | Week 24 [11/03] | Week 25 [18/03] | Week 26 [25/03] | Week 27 [01/04] | Week 28 [08/04] | Week 28 [15/04] | Week 29 [22/04] | Week 30 [29/04]
[5 empty] | (deadline / event) |  | Project brief | [8 empty] | Progress report | Christmas break |  |  |  | Exams | [14 empty] | Final report
Background
Literature review
Researching ML algorithms
Learning how to use Python tools
Design (requirements, specification)
Implementation
| 45215 |  |  | Data exploration and visualisation
| 45406 |  |  | Iterative development prototype 1
Prototype 1 evaluation and improvements
Iterative development prototype 2
Prototype 2 evaluation and improvements
Iterative development prototype 3
Prototype 3 evaluation and improvements
Testing and validation
Report writing
Progress report
Final report
Formulas:
End date = [Start date]+[Duration (days)]